General Software
Solution Assurance Checklist
for a
Technical and Delivery Assessment (TDA)

Version 4.0
awes@se.ibm.com
Updated December 20, 2014

Abstract: This document is meant to assist the Subject Matter Expert (SME) and Quality Practitioner in preparation for and during a Technical and Delivery Assessment (TDA).

IBM Business Partners:
The Solution Assurance information, tools and documentation (“Materials”) are being provided to IBM Business Partners to assist them with customer installations. Such Materials are provided by IBM on an “as is” basis. IBM makes no representations or warranties regarding these Materials and does not provide any guarantee or assurance that the use of such Materials will result in a successful customer installation. These Materials may only be used by authorized IBM Business Partners for installation of IBM products and otherwise in compliance with the IBM Business Partner Agreement.

Table of Contents
How to use this document
This document helps the SME (Subject Matter Expert) and the QP (Quality Practitioner) to ensure all aspect of a proposed solution is assessed during the TDA review.
This document is NOT meant to be used for documenting the solution itself. The Opportunity team is expected to provide solution description as input to the TDA to the SME(s) in TeamSD or similar documentation.

# Introduction
This document assists the IBM Solution Assurance Quality Practitioner or Business Partner in preparing for an IBM Technical and Delivery Assessment (IBM TDA). The Opportunity Owner as defined in Sales Connect is the owner of the TDA.
The document draws attention to the critical considerations for successful delivery of the proposed solution throughout an enterprise.

IBM requires a pre-sales team to answer the following fundamental questions, before releasing the proposal to the client, through this IBM TDA process.
- Will it work? Will the customer buy it?
- Does our solution meet the customer’s requirements and expectations?
- Have we over/under engineered the solution? Is it optimized?
- Is the delivery plan complete, including key short and long term activities, milestones etc.?
- Is the team in place to deliver and manage the solution into production? Based where?
- Have we spotted and covered key risks, issues, assumptions and dependencies?
- How long will it take to deliver? How do we know? Do timings meet customer expectations?
- Can we run and support it? Can we reduce our costs over time?
- So what could possibly go wrong? … And if it does, what happens...?

This checklist is provided as a guide for the following areas:
- Customer Requirements
- Solution Design and Specification
- Implementation Project and Client Readiness
- Run and Operate – Managed IT Service

Depending on the stage of engagement not all activities need to be completed during the Technical Delivery and Assessment. However, if not all activities are answered then plans must be put in place to address risks and issues associated with these topics prior to installation of the solution. This may start with revising the scope of proposal.
# Opportunity Information
Customer Name:
TDA Date:
Revenue:
Sales Connect #:
Solution Description (Summary):

# Pre-Review Checklist
Item or Person required at the Review	Reference or Name
Documents describing customer requirements
Documents describing the proposed solution
SME for each technology area in the solution
Opportunity Owner
Technical Owner or Technical Team Lead responsible for the design of the solution
Description of performance guarantees, if applicable
Services provider or description of proposed services

# Attendees and Roles
Role	Person
Quality Practitioner
Opportunity Owner
Technical Owner/Technical Team Lead
Subject Matter Expert(s)
AVP Manager (if applicable)
Etc…

# Customer Requirements
ID	Activity	Yes / No / NA	Evidence Reference	Evidence Quality	Note
5.1	Has a client organization and/or executive sponsor or been identified and engaged? / (e.g. TeamSD Project Definition)
5.2	Have the customer’s business objectives and benefits been communicated, understood and documented? / (e.g TeamSD Business Model)
5.3	Are the assumptions and customer constraints and risks understood and documented? / (e.g. TeamSD Viability Assessment)
5.4	Have the customer’s baseline functional and non-functional requirements (FRs & NFRs) been documented and traced back to the business objectives? e.g. FRs and NFRs such as / Functional / Operational / Volumes and Performance / Scalability and Load Balancing / Availability / Data Privacy and Security. / Service Levels / maintenance / (e.g. TeamSD Requirement Matrix, Use-case Model and NFRs )
5.5	Does the customer have to comply with country, local or industry specific regulations or standards? / E.g. PCI, SOX, HIPAA / (e.g. TeamSD Standards)
5.6	Are the customer’s geographic locations, languages and times zone requirements defined? / (e.g. TeamSD Project Definition)
5.7	Are the customer’s existing systems or environments impacted by these new requirements? (i.e.Systems could be on and/or off premise hosting). / (e.g. TeamSD Current IT Environment)
5.8	Have the baseline requirements been walked through with all key stakeholders and agreed by the customer? / (e.g. TeamSD Requirements)

# Solution Design and Specification
ID	Activity	Yes / No / NA	Evidence Reference	Evidence Quality	Note
6.1	Has the overall architecture of the solution been documented and communicated to the customer? / (e.g. TeamSD Architectural work products including the System Context and AOD)
6.2	Does the design meet the functional and non-functional requirements? / (e.g. TeamSD Requirement traceability Matrix)
6.3	Have you validated that the major functional use cases and requirements are supported by the proposed system architecture? / E.g. map use cases / function and system components / (e.g. TeamSD Use Case Model Requirement Matrix, component model and operational model)
6.4	Does the design meet the performance, availability, and scalability requirements? / (e.g. TeamSD NFRs and Operational Model)
6.5	Has the solution considered how it will communicate / integrate with existing and has this been identified and documented? / (e.g. TeamSD System Context AOD, Component Model, Operational Model)
6.6	Has the data architecture been defined (e.g. data flows and store). / Have you taken into consideration data? / (e.g. TeamSD Subject Area Model)
6.7	Are plans for migration of current applications needed? / (e.g. TeamSD Strategic Roadmap)
6.8	If migrating to a new product level, has the customer reviewed all available migration information for migrating planning assistance? / (e.g. TeamSD Strategic Roadmap)
6.9	Does the customer have a fall back plan if migration is not successful?
6.10	Have systems management systems and procedures (backup / recovery, server monitoring, problem management and change management) been identified and defined? / (e.g. TeamSD NFRs and Operational Model)
6.11	Does the design meet upgradeability requirements? / (e.g. TeamSD Project Definition)
6.12	Does the design meet the data privacy and security requirements? / (e.g. TeamSD NFRs, Component Model, Operational Model)
6.13	Has this proposed solution been successfully implemented before? Where? By whom? Or is it a First Of A Kind(FOAK). / (e.g. TeamSD Candidate Assets)
6.14	Is a benchmark or proof of concept required? If so has it been resourced and funded?
6.15	Has the specified IBM Software and Hardware configuration been defined, sized, traced to the requirements and verified by relevant subject matter experts? / (e.g. TeamSD Specified Operational Model)
6.16	Has the specified non-IBM Software and Hardware configuration been defined, sized, traced to the requirements and then verified by a relevant subject matter experts? / (e.g. TeamSD FRs and NFRs Specified Operational Model)
6.17	Have the appropriate versions of all required Software been included? Reference the document containing the List of Software versions here. / (e.g. TeamSD FRs and NFRs Estimation Report)
6.18	Has software and hardware compatibility been checked? Identify any issues or concerns here. / (e.g. TeamSD Viability Assessment)
6.20	Has the customer planned for connectivity options from all locations
6.21	Is the appropriate network infrastructure in place or planned to be in place (routers, firewalls, cabling etc.)?
6.22	What hardware maintenance is required?
6.23	When specifying all the Hardware and Software have the following been taken into consideration? / Cost / Number of users, applications, nodes, partitions, etc. / Footprint (physical size of the servers) / Scalability and high availability / The number of servers required to support the solution to support the volumetric / Is redundancy required for each server / Does the fully configured server allow for the agreed volumetric. / Will the planned configuration provide the required throughput and response time for the volumetric? / (e.g. TeamSD Viability Assessment)
6.24	Does the design or solution depend on unannounced products? If yes, identify the design or solution. / How will the customer get support for unannounced products? / What is that products future IBM roadmaps?
6.25	What sources of IBM Intellectual Property, Patents, Software Assets and best practice guidance was used to design this solution – i.e., Development Guides, Redbooks, Lab.

# Implementation Project & Client Readiness
	Activity	Yes / No / NA	Evidence Reference	Evidence Quality	Note
7.1	Has Project Governance been defined, communicated and agreed with all parties? / E.g. .have you considered the technical Quality Assurance reviews, Day 1 Plan, Project Office, Change management
7.2	Has a method adoption workshop to consider project standards, methods and processes been run and agreed across all parties? / E.g. IBM Method, Agile, Waterfall, PMP
7.3	Is the project “doable” in the necessary time and budget / costs to meet the customer’s objectives? / e.g. IBM Method, PMP
7.4	Has a single delivery project plan, documenting deliverables (activities, milestones, duration, resources, and dates) been defined and agreed internally and externally? / e.g. IBM method, PMP
7.5	Have at least two appropriate estimating methods been used to size the project plan activities and tasks? / e.g. IBM Method, PMP, Estimating techniques
7.6	Are the customer’s staffing and trained resources in place for the duration of the project?
7.7	Are IBM staff and trained resources in place for the duration of the project?
7.8	Have the Business Partners (IBM GTS/GBS/External) and / or subcontractors names and commitments been identified and agreed?
7.9	Have all resources, including IBM, business partner and subcontract or quality, expertise and integrity been assessed and is it acceptable?
7.10	Have considerations been made to deliver the project over a number of releases and is the plans aligned with these releases?
7.11	Have test and acceptance plans been defined and agreed?
7.12	Have you thought about how you are going to transition this project into a live production service?
7.13	Are the project and technical risks, assumptions, issues and dependencies (RAID) understood, communicated and documented across all parties.
7.14	Have the technical teams provided the work breakdown and estimates?
7.15	Has a walkthrough of the project plan been held with all key internal and external stakeholders?

# Run and Operate - Managed IT Service
ID	Activity	Yes / No / NA	Evidence Reference	Evidence Quality	Note
8.1	Has an agreement been reached as to who will provide implementation services for the managed service? / (e.g. Readiness Plan)
8.2	Has a managed service provider provided a quote and has this been included in the proposal? / Does the managed service provider have the capabilities and resources required to manage the service? / (e.g. Readiness Plan)
8.3	If more than one managed service provide provider (Customer, BP or IBM) is involved, is it clear who is responsible for what? / Is the exit criteria clear? / (Contract T&Cs)
8.4	Has a post-sales support contract been included in the proposal to cover operational hours? / (e.g. Readiness Plan)
8.5	Has the solution included a Service Definition that defines ‘As a Service’? Including the service level agreements, roles and responsibilities, and skills required to the run and operate the system for the duration of the managed IT service contract? / Is it explicitly stated who will be responsible for providing the IT service This includes defining the service management processes, tools and services for Operations/ Change / Problem / Performance / Availability / Capacity planning / Operations / Security Administration. / e.g. Service Definition, Contract T&Cs
8.6	Are there any formal acceptance criteria defined by the customer for formally accepting the system into service If so, who owns them and have sufficient resources been allocated to meet them.
8.7	Have Service Management and Application Support teams contributed to the Solution Design?
8.8	Has a customer communications, training and education plan been defined and documented? / (e.g. Readiness Plan)
8.9	Has the customer been provided with the IBM Software Support Handbook and understand how to engage IBM Support Services / Line appropriately? / (e.g. Readiness Plan)
8.10	Does a Customer Support Plan (CSP) or any other support documentation need to be delivered to the customer? / (e.g. Readiness Plan)

# Additional Information
	Activity	Yes / No / NA	Evidence Reference	Evidence Quality	Note
9.1	Is there any other useful information the Quality Practitioner or SME’s need to be aware of?

# Action Item List

From Question #	Action Item	Owner	Due Date	Complete Date

# Assessment Definition
Use the following values to score the quality of the evidence.
Indicator	Definition
n/a	Not adopted
1	Very poor or non-existent
2	Poor
3	Basic – communicates the necessary minimum
4	Good
5	Exemplary

# Evidence Reference
Please list below the pre-sales artifact and the location that support your answers to the TDA. Please add any additional work products / deliverables.

ID.	Work Product / Deliverable	Location	Reviewers
	RFI / RFP
	Customer Requirements
	Project Change Log
	Project RAID
	Team Solution Design
	Project Management Plan
	Bill of Materials / Pricing
	Proposal
	Contract
	Stakeholder Signoffs

# Document Change Control
Version	Changes
V1.1	Added additional columns on the Action Item table: Owner, Due Date and Complete Date
V2.0	Fixed document corruption
V2.1	Corrected spelling of Siebel
V2.2	Re-type of the entire document to fix document corruption problem
V2.3	Content re-organized and updated
V3.0	Updated instructions, included references to TeamSD where appropriate, and merged old section “Product/Solution Capability” with the Solution Design section.
V4.0	Updated in several places. Questions related to designing and delivering XaaS solutions added.

End of document.